## README
AutoDock — planning workbook
Project: AUTODOCK — AutoDock
Workstreams: EE = Electronics and ELectrical Designing, MEC = Mechanical Designing, PC = Procurement, ROS = Robot Software and Development
Fill the sheets in order. Each one depends on the names you used in the one before it.
1. Team people who will own or review work. Skip anyone already listed on Reference.
2. Milestones the checkpoints inside each workstream.
3. Deliverables optional. Named outputs under a milestone. Skip the sheet entirely if you
do not need this level.
4. Tasks the actual work. This is the sheet that matters most.
5. Supply optional. Long-lead orders and supply risks, so they can be watched.
Rules
RED header = required. The row is rejected without it.
BLUE header = optional. Leave it blank if you do not know yet.
Blank is a real answer. An empty Owner or Priority is loaded as "not decided yet" and shows up
on the clarification queue for you to resolve in the app. Nothing is ever guessed or filled in
on your behalf — so do not put a placeholder in just to fill the cell.
Row 3 of every sheet is a grey EXAMPLE row. It is ignored on import. Delete it or type over it.
Names are the link between sheets. A task finds its milestone by typing the milestone name
exactly as written on the Milestones sheet, for the same workstream. Dropdowns are wired up
where possible, so prefer picking over typing.
Dates: YYYY-MM-DD (e.g. 2026-10-20).
The one constraint to know about
A task must have a start date and a due date, and may span at most 3 calendar days.
If a task covers more than one day, every day needs its own outcome (the Day 1..3 columns),
so a multi-day task is several checkable outcomes rather than one vague block of time.
This means long work has to be broken down before it can be entered. If that does not suit how
you want to plan, say so — the limit is one setting (MAX_TASK_SPAN_DAYS) and the requirement for
dates at all is a few lines of code. Both are easy to change; neither should be worked around by
putting fake dates in.
When you are done
Save the file and hand it back. It gets loaded in one pass: team first, then milestones,
deliverables, tasks, supply. You will get a report of what was created and anything that could
not be resolved. Nothing is written until the whole file validates.

## Team
People to add. Anyone already in the system is listed on the Reference sheet — do not repeat them here.
Name | Email | Role | Title
EXAMPLE - delete this row | example@vegam.co | employee | Mechanical Engineer
Note on A2: Full name as it should appear in the app.
Note on B2: Must be unique. This is how tasks on the Tasks sheet point at an owner.
Note on C2: manager = can create tasks, set deadlines, manage the team. employee = works on and updates their own tasks.
Note on D2: Optional job title, shown on the roster.

## Milestones
Checkpoints inside each workstream. A milestone groups tasks; it is not itself a task.
Workstream | Milestone Name | Description | Start Date | End Date | Target Date | Timeline Label | Long-Lead Items / Risks
EXAMPLE - delete this row | Chassis frame complete | Welded frame, squared and load-tested |  |  |  | W1 - W3 | Aluminium extrusion - 3 week lead
Note on A2: Code from the Reference sheet: EE, MEC, PC, ROS
Note on B2: Must be unique within the workstream. Tasks and deliverables refer back to this exact text.
Note on C2: What 'done' means for this milestone.
Note on D2: YYYY-MM-DD. Optional.
Note on E2: YYYY-MM-DD. Optional.
Note on F2: The date being committed to, if different from End Date.
Note on G2: Free text for a relative schedule, e.g. 'W1 - W3'. Kept verbatim.
Note on H2: Constraints and dependencies, one per line (Alt+Enter). Anything with a date belongs on the Supply sheet instead.

## Deliverables
OPTIONAL SHEET. Only use it if you want a layer between a milestone and its tasks. Leave empty otherwise.
Workstream | Milestone Name | Deliverable Name | Description | Due Date | Due Label | Critical
EXAMPLE - delete this row | Chassis frame complete | Load test report | Signed-off test sheet |  | by W3 | no
Note on A2: Code from the Reference sheet.
Note on B2: Must match a Milestone Name on the Milestones sheet, in the same workstream.
Note on C2: The named output.
Note on D2: Optional detail.
Note on E2: YYYY-MM-DD. Optional.
Note on F2: Free text, e.g. 'by W2'. Kept verbatim.
Note on G2: yes = flagged as a critical long-lead item.

## Tasks
The work itself. Every task needs a workstream, a title, and a start and due date.
Workstream | Milestone Name | Deliverable Name | Task Title | Description | Owner Email | Reviewer Email | Supporters (emails, comma-separated) | Priority | Start Date | Due Date | Day 1 Outcome | Day 2 Outcome | Day 3 Outcome | Next Action | Depends On (task titles)
EXAMPLE - delete this row | Chassis frame complete |  | Cut and square extrusion for base frame | All 8 members cut to drawing, ends faced | rani@vegam.co |  |  | P1 |  |  | Cut all 8 members to length |  |  | Confirm stock on hand
Note on A2: Code from the Reference sheet. This is the only required parent.
Note on B2: Optional. Must match the Milestones sheet exactly, same workstream. Blank = task sits directly under the workstream.
Note on C2: Optional, and only if a Milestone Name is given.
Note on D2: Short, specific, one piece of work.
Note on E2: Detail, acceptance criteria, links.
Note on F2: The single accountable person. Blank = unassigned, raised as a clarification.
Note on G2: Optional. Who signs the work off.
Note on H2: Optional helpers. The owner stays singular and accountable.
Note on I2: P0 = drop everything ... P3 = whenever. Blank = not decided, raised as a clarification.
Note on J2: YYYY-MM-DD. Required.
Note on K2: YYYY-MM-DD. Required, and at most 3 calendar days from the start (inclusive).
Note on L2: What day 1 of this task produces. Required if the task spans 1 or more days.
Note on M2: What day 2 of this task produces. Required if the task spans 2 or more days.
Note on N2: What day 3 of this task produces. Required if the task spans 3 or more days.
Note on O2: The immediate next step, if known.
Note on P2: Titles of other tasks in this sheet, comma-separated. They do not have to appear above this row.

## Supply
OPTIONAL SHEET. Long-lead orders and supply risks. An order placed late arrives late and nothing else can move — this is what lets the system warn you in advance.
Workstream | Milestone Name | Item | Kind | Lead Time (weeks) | Order By | Needed By | Status | Owner Email | Critical | Note
EXAMPLE - delete this row | Chassis frame complete | VFD unit | order | 8 |  |  | not_ordered |  | yes | Quote pending from vendor
Note on A2: Code from the Reference sheet.
Note on B2: The milestone this item belongs to. Supply items hang off a milestone.
Note on C2: What is being ordered, or the risk being tracked.
Note on D2: order = something to place by a date. risk = a constraint with no order to place.
Note on E2: Whole weeks from order to arrival.
Note on F2: YYYY-MM-DD. Leave blank and it is worked back from Needed By minus the lead time.
Note on G2: YYYY-MM-DD. The latest it can arrive and still be usable. Without this, lateness cannot be judged.
Note on H2: not_ordered / ordered / received / not_needed. Blank = not_ordered.
Note on I2: Who is chasing it.
Note on J2: yes = schedule stops without it.
Note on K2: Vendor, quote reference, anything useful.

## Reference
Read-only. Generated from the live system — do not edit.
Workstream Code | Workstream Name | Existing Member | Email | Role / Priority / Status values | All emails (owner dropdown)
EE | Electronics and ELectrical Designing | Rani | rani@vegam.co | Roles: manager, employee | rani@vegam.co
MEC | Mechanical Designing |  |  | Priority: P0, P1, P2, P3
PC | Procurement |  |  | Supply kind: order, risk
ROS | Robot Software and Development |  |  | Supply status: not_ordered, ordered, received, not_needed
Max task span: 3 calendar days
Dates: YYYY-MM-DD